## Sheet1
The main contractor distribution of site work normally the equipment must be on site during the whole period be the main contractor's responsibility. It is only there for short periods of time are trade contractors responsibility | Main contractor | Soil work | sewer work | Concrete work | masonry work | Element work | Capentry work | Electicien work | Plumber work | Ventlilatonsentreprisen | steel work | painting work | orther | orther
Number of units indicatedto the specific trade
Sanitary cabin
Dining cabin
Formann carbin
Meating carbin
Electricity connection to the carbins
Sewer connection to the carbins
Water connection to the carbins
Internet connection
El-tracing vand til skure
El-tracing byggevand
Water in the building period
lighting building site
light poles building site
Crane
Crane driver
Fence
Gate
Outdoor cleaning
Opening and close building site
Surveying
Container burnable
Container heavy
Container steel
Container mixed
Container burnable
Steel sheets building site road
Scaffolding
Interim stairs
Lifts
Lifts for persons
Cleanup own work
Outdoor cleaning
Buildig site signs
Heating up cabins
Final cleaning